## Sheet1
Task No |  | Duration | Predecessor
1 | Scope
2 | Determine project scope | 4 days |  | Start Date Jan 12, 2026
3 | Secure project sponsorship | 2 days | 2
4 | Define preliminary resources | 2 days | 2
5 | Secure core resources | 2day | 2
6 | Analysis/Software Requirements
7 | Conduct needs analysis | 5 days | 5
8 | Draft preliminary software specifications | 3 days | 5
9 | Develop preliminary budget | 2 days | 7
10 | Review software specifications/budget with team | 2 days | 7
11 | Incorporate feedback on software specifications | 2 days | 10
12 | Develop delivery timeline | 2 days | 10
13 | Obtain approvals to proceed (concept, timeline, budget) | 4 days | 10
14 | Secure required resources | 2 days | 11
15 | Design
16 | Review preliminary software specifications | 2 days | 11
17 | Develop functional specifications | 5 days | 16
18 | Develop prototype based on functional specifications | 4 days | 17
19 | Review functional specifications | 2 days | 18
20 | Incorporate feedback into functional specifications | 2day | 19
21 | Obtain approval to proceed | 2 days | 20
22 | Development
23 | Review functional specifications | 2 days | 19
24 | Identify modular/tiered design parameters | 2 days | 23
25 | Assign development staff | 2 days | 24
26 | Develop code | 15 days | 25
27 | Developer testing (primary debugging) | 15 days | 26
28 | Testing
29 | Develop unit test plans using product specifications | 4 days | 27
30 | Develop integration test plans using product specifications | 4 days | 27
31 | Unit Testing
32 | Review modular code | 5 days | 30
33 | Test component modules to product specifications | 2 days | 32
34 | Identify anomalies to product specifications | 3 days | 33
35 | Modify code | 3 days | 34
36 | Re-test modified code | 2 days | 35
37 | Integration Testing
38 | Test module integration | 5 days | 36
39 | Identify anomalies to specifications | 2 days | 38
40 | Modify code | 3 days | 39
41 | Re-test modified code | 2 days | 40